## Instructions
INSTRUCTIONS TO COMPLETE THIS BUDGET TEMPLATE
| Which worksheets to complete | This budget template includes three worksheets which need to be completed by applicants: ► Summary Budget ► Workplan ► Detailed Budget
The Summary Budget worksheet is where you should enter the general data about the proposed BPP initiative in the text fields in red. Please note that the rest of the Summary Budget figures will auto-populate based on your entries in the Detailed Budget worksheet.
| Recommended steps in completing the template | Some cells have fixed formatting and should not be adjusted unless necessary. Rows can be added/eliminated as neededed ensuring the formatting remains intact. It is recommended to double check formulas in fixed formatted cells for accuracy.
| Information sources | In case of technical difficulties in using this template or about any aspect of this template contact us at applications@thebpp.com.au for assistance.
SUMMARY BUDGET
| Column header | Instructions | Comments
| Organisation Name | Enter the legal name of your organisation
| Country | Enter the country of implementation of the proposed BPP initiative
| Initiative Title | Enter the proposed title of your initiative, consistent with what you inserted in the application form
| Application Reference Number | Enter your BPP application number | Refer to application number generated in Smartygrants.
| Funding start date | Enter Day, Month and Year (numeric values) for the intended start of the funding period. | For the India Window this must be between 1/10/2018 and 31/12/2018
| Indicative Milestone Payments | List key activities comprising each milestone and verification requirements for each activity | NOTE: This should be the last step to complete once the Detailed Budget and Workplan worksheets have been fully populated.
WORKPLAN
|  | Instructions | Comments
| ALL rows and columns | The Workplan worksheet can be customised to fit the initiative's logical framework. Please ensure to breakdown the activities in your work plan in a logical sequence (objective, activity, output/deliverable, milestone)
| ALL rows and columns | Plot when the activities will take place throughout the initiative’s lifecycle. Make sure outputs/milestones are appropriately spread throughout each six month interval.
| First row (Initiative title and timeline) | This row will self-populate with the title and dates entered in the summary budget tab
DETAILED BUDGET
| Column header | Instructions | Comments
| GENERAL instruction | Plot activities under each budget heading section with same indexation and numbering as the Workplan. | Please refer to the budget heading description table.
| Activity | In the column you should describe clearly and concisely, the planned budget activity. | The wording, numbering and indexing should be consistent with that used in the Workplan worksheet.
| Contribution Type | Indicate the type of contribution (cash or in-kind) pertaining to partner contributions. If a type of contribution is part cash, part in-kind, select the contribution type with the highest proportion and make a note on column titled “budget assumptions”. | Note: Ensure there is consistency with the information entered in the application form
| Unit Type | This is the unit of measurement to which the unit cost (in the next column) refers. Please select an option from the drop down menu that best fit the nature and costing method of the activity. | Applicants should explain the detailed assumptions of costs in the column "detailed budget assumptions"
| Unitary Cost (AUD) | This is the unit cost of the item described in the preceding column in AUD currency | Budget assumptions should provide sufficient information to be able to determine how unit costs were calculated. If the item is costed in a currency other than the proposed currency, the working to convert the unit cost to the defined currency should be shown in the "Detailed budget assumptions" column. If there is a differential unit cost for the same activity line in the same period then a separate row should be added in the budget, and the calculation explained in the "Detailed budget assumptions" column.
| DFAT Contribution | Indicate the activities that will be funded with DFAT’s contribution. Cost amounts should be broken down per semester (six month period), by multiplying unit cost by quantity nedded per semester. | Acronym S1Y1 stand for Semester 1, Year 1
| DFAT | This is a formula which auto-calculates DFAT's total contribution by adding six-monthly contributions.
| Lead Partner | Indicate the activities that will be funded by the Lead Partner. Enter the total amount to fund or co-fund the activity. The contribution of partners do not need to be broken down per semester. | Lead Partner – the partner who will take key ownership of the initiative and will be the main point of contact between the partnership and the BPP Fund Manager. The lead partner will enter into the contractual agreement with the BPP Fund Manager and may be subject to additional due diligence. Should two or more organisations apply together, one partner must be nominated as the lead partner.
| Other Partner(s) | Indicate the activities that will be funded by other partners included in your application. Please aggregate the contribution of other partners if more than one other partner/investor/donor exists apart from the Lead Partner. Enter the total amount to fund or co-fund the activity. The contribution of partners do not need to be broken down per semester. | Other Partners – others who are visibly and materially involved in achieving the partnership outcomes. Other partners often have significant roles implementing the initiative.
| TOTAL | This is a formula which auto-calculates the total cost of the initiative (DFAT + Partners + Other partners)
| Matched-Funding (%) | This is a formula which indicates the percentage of funding that partner will co-contribute calculated per each individual activity and per cost category. | It is not necessary to match funding per activity or cost category. The make up of match funding will vary depending on the nature of the project. However a uniform 50/50 spread across cost categories will indicate a more equal risk sharing.
| Detailed Budget Assumptions: | Indicate the calculation used and any other detail where it would enhance understanding. | Applicants should supply detailed budget assumptions where it will enhance understanding. The notes should explain: (i) why a particular item/service/human resource is needed (ii) what is the cost basis (e.g. based on quotes, market research, historical costs), and (iii) the calculation used
COST CATEGORY DESCRIPTIONS
| Cost Category | Description
| Program Activity Cost | Expenditure related to per diems, accommodation, meals, meetings, workshop costs, publication costs, training costs, printing costs, field visits and other costs relating to program planning, supervision, and monitoring and evaluation.
| Operational Costs | Operational expenditure and administrative expenses for overall administration of the program. This includes office rent, utilities, internal
communication costs (mail, telephone, internet), office supplies, administration cost, fuel, legal costs , translation costs, accounting and auditing costs, and bank charges.
| Capital Expenditure | This includes the cost of procuring or maintaining productive assets such as information technology (IT) systems, machinery, infrastructure, office equipment, furniture, audio-visual equipment, generators, technical equipment, motorbikes, computers, etc.
| Personnel costs | This include both administrative and program personnel involved in the initiative (including field personnel and volunteers). This includes salaries, wages, stipends, allowances, and consulting fees.
| Other costs | Costs which do not fall under the above-defined categories. The applicant is encouraged to avoid using this category unless it is deemed necessary. Applicant must provide a detailed description of the items that have been classified under this category.
ITEMS THAT CAN BE FUNDED BY THE BPP/DFAT
Note: the below table is a guide only. Items to be funded will be subject to final contract negotiations.
| Generally Acceptable | Possible Funding | Unable to Fund
| · Attributable technical specialist support | · Physical assets, e.g., machinery or infrastructure | · Management fees
| · Related staff salaries (relating to development & start up) | · Recurring operational and working capital costs of partner, including personnel | · Free/discounted samples
| · Related vehicle expenses | · Audits | · Inputs manufactured by the partner (e.g. for use on demo plots)
| · Related training costs | · Related equipment and supplies (printer, laptop, camera, motorbike) | · Fundraising
|  | · Telephone and IT for BPP use only | · Advocacy (unless specific to the BPP objective then should be attributable)
|  | · Office supplies and equipment | · Marketing and communications (unless specific to the BPP initiative then should be attributable)
|  | · Office rental, maintenance, electricity, water and printing | · Retroactive expenses: i.e. costs incurred prior to the effective funding start date of the contract
· Taxes and import duties applied by governments and public authorities
TYPES OF IN-KIND CONTRIBUTIONS GENERALLY ACCEPTED UNDER THE BPP
Note: the below table is a guide only. Items to be funded will be subject to final contract negotiations.
| Generally Acceptable | Unlikely to be Acceptable
| · Volunteer hours | · Costs (or other) non-related to the BPP initiative
| · Equipment, materials and supplies | · Costs (or other) currently funded by the partner or other donors
| · Legal assistance | · Any non-preapproved/agreed costs
| · Overhead/administration costs (maximum 5%) | · Other DFAT funding
· Salaries
· Professional and technical services
· Travel and subsistence costs
· Technology
· M&E including dissemination of data/information
· Office and work-space

## Summary Budget
General Information
Organisation Name: | Palladium International
Country: | India
Initiative Title: | Enhancing livelihoods for farmers in Maharashtra
Application Reference Number: | BPPR2484
| dd | mm | yyyy
Funding start date: | 1 | 1 | 2019 |  | Initiative Duration : |  | 24
BPP Funding Period: |  |  | Year 1 |  | Year 2
|  |  | Y1S1 | Y1S2 | Y2S1 | Y2S2
From: |  |  | 2019-01-01 | 2019-07-01 | 2020-01-01 | 2020-07-01
To: |  |  | 2019-06-30 | 2019-12-31 | 2020-12-31 | 2020-12-31
BPP/DFAT FUNDING REQUEST BUDGET SUMMARY | [5 empty] | PARTNER CONTRIBUTION BUDGET SUMMARY |  |  |  | Contribution (%) | PARTNER CONTRIBUTION BREAKDOWN
Program Activity Costs |  | 14320 |  |  |  | Program Activity Costs |  | 0 |  | 0% | Cash | 121896
Operational Costs |  | 2640 |  |  |  | Operational Costs |  | 43600 |  | 94.29% | In-Kind | 76800
Capital Expenditure |  | 3296 |  |  |  | Capital Expenditure |  | 6296 |  | 65.64% | Cash Proportion | 61.35%
Personnel Costs |  | 144000 |  |  |  | Personnel Costs |  | 148800 |  | 50.82%
Othe Costs |  | 0 |  |  |  | Othe Costs |  | 0
TOTAL FUNDING REQUEST: |  | 164256 |  |  |  | TOTAL CO-CONTRIBUTION: |  | 198696 | MATCHED-FUNDING RATIO | 1: 1.21 | TOTAL INITIATIVE COST: | 362952
INDICATIVE MILESTONE PAYMENT DETAILS: | [5 empty] | LIST KEY ACTIVITIES COMPRISING EACH MILESTONE (Refenced by Activity Number AND including those activities funded by Partners) |  |  |  |  | LIST VERIFICATION REQUIREMENTS PER EACH MILESTONE:
Milestone Payment 1 |  | 39660 |  |  |  | Act 1.Recruitment of key staff Act 4.Completion of baseline survey |  |  |  |  | Act 1.Written confirmation of employment and resumes of employed staff Act 4.Submission of baseline survey report
Milestone Payment 2 |  | 51276 |  |  |  | Act. 6. Completion of inception workshops Act 8. Training to 300 farmers completed |  |  |  |  | Act 6.Attendance sheets, copies of workshop materials, photographs of workshop events. Act 8.Training signing sheets, copies of training materials, photographs of training events.
Milestone Payment 3 |  | 36660
Milestone Payment 4 |  | 36660
Formulas:
yyyy = IFERROR(EDATE([yyyy, row above],6)-1,"")
Y1S2 = IFERROR(EDATE([yyyy],6),"")
Y1S2 = IFERROR(EDATE([yyyy, row above],12)-1,"")
Year 2 = IF(J10<=12,"",EDATE([yyyy],12))
Year 2 = IF(J10<=12,"",EDATE([yyyy, row above],J10)-1)
Y2S2 = IF(J10<=18,"",EDATE([yyyy],18))
Y2S2 = IF(J10<=18,"",EDATE([yyyy, row above],J10)-1)

## Workplan
| YEAR 1 | [11 empty] | YEAR 2
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
Workplan for Initiative: Enhancing livelihoods for farmers in Maharashtra | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
1) Objective 1: New market development for agriculture seeds and inputs
Activity 1.Recruitment of one Program Manager | bar: 2019-01-01
Activity 2.Recruitment of one Program Officer | bar: 2019-02-01
Activity 3.Engagement of external consultant to prepare baseline survey | bar: 2019-03-01 to 2019-04-01
Activity 4. Completion of baseline survey by consultant | bar: 2019-05-01
Milestone 1. Recruitment of key staff completed and completion of baseline survey | bar: 2019-06-01
Activity 5. Develop communication materials for the inception workshops | bar: 2019-07-01 to 2019-08-01
Activity 6. Conduct demonstration workshops in 8 communities | bar: 2019-08-01 to 2019-10-01
Activity 7. Organise training events and develop training materials for farmers | bar: 2019-11-01
Activity 8. Conduct training to 300 farmers | bar: 2019-11-01 to 2019-12-01
Milestone 2. Completed inception workshops at the community level and Training to 300 farmers | bar: 2019-12-01
2) Objective 3
Activity 7
Activity 8
Activity 9
Activity 10
Activity 11
Activity 12
Milestone 3
3) Objective 4
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Milestone 4

## Detailed Budget
Budget detail for initiative: Enhancing livelihoods for farmers in Maharashtra |  |  |  | DFAT Contribution (Only DFAT Contribution) |  |  |  | Total Initiative Budget (Including DFAT and Partner's contribution) |  |  |  |  | Detailed Budget Assumptions:
Activity | Contribution Type | Unit Type | Unitary Cost (AUD) | Y1S1 | Y1S2 | Y2S1 | Y2S2 | DFAT | Lead Partner | Other Partner(s) | TOTAL | Match-Funding (%) | Applicants should supply detailed budget assumptions where it will enhance understanding. The notes should explain: (i) why a particular item/service/human resource is needed (ii) what is the cost basis (e.g. based on quotes, market research, historical costs), and (iii) the calculation used
Personnel Costs
Project Accountant 0.4 FTE | In-Kind | Monthly Cost | 3200 |  |  |  |  | 0 | 76800 |  | 76800 | 100% | Monthly Salary 8000 AUD * 0.4 FTE for 24 months -base on current salary
Project Manager 1 FTE | Cash | Monthly Cost | 6000 | 36000 | 36000 | 36000 | 36000 | 144000 |  |  | 144000 | 0% | Salary Full time AUD 6,000 based on local current market rate.
Project Officer 1 FTE | Cash | Monthly Cost | 1800 |  |  |  |  | 0 | 43200 |  | 43200 | 100% | Full time project officer for 1800 AUD per month for 24 months
Monitoring and Evaluation Specialist (Consultancy) | Cash | Daily Cost | 360 |  |  |  |  | 0 |  | 28800 | 28800 | 100% | 80 days input of M&E specialist at a daily rate of 360 AUD
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 | -
|  |  | 0 |  |  |  |  | 0 |  |  | 0 | -
Personnel Cost Sub-Total: |  |  |  | 36000 | 36000 | 36000 | 36000 | 144000 | 120000 | 28800 | 292800 | 50.82%
Activity | Contribution Type | Unit Type | Unitary Cost (AUD) | Y1S1 | Y1S2 | Y2S1 | Y2S2 | DFAT | Lead Partner | Other Partner(s) | TOTAL | Match-Funding (%) | Detailed Budget Assumptions:
Operational Costs
Communication costs (Internet, phone service) | Cash | Monthly Cost | 110 | 660 | 660 | 660 | 660 | 2640 |  |  | 2640 | 0% | Budget based on AUD15 stationary, AUD15 other office supplies, AUD10 telephony, AUD60 internet, and AUD10 for ink cartridges, printing/photocopying per month. Estimated costs based on historical costs
Vehicle Maintenance | Cash | Annual Cost | 800 |  |  |  |  | 0 | 1600 |  | 1600 | 100% | Annual cost for 1 vehicle -Based on historical costs
Office Rent | Cash | Monthly Cost | 1500 |  |  |  |  | 0 | 36000 |  | 36000 | 100%
Vehicle Fuel | Cash | Monthly Cost | 250 |  |  |  |  | 0 | 6000 |  | 6000 | 100%
[9 empty] | 0 |  | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
Operational Costs Sub-Total: |  |  |  | 660 | 660 | 660 | 660 | 2640 | 43600 | 0 | 46240 | 94.29%
Activity | Contribution Type | Unit Type | Unitary Cost (AUD) | Y1S1 | Y1S2 | Y2S1 | Y2S2 | DFAT | Lead Partner | Other Partner(s) | TOTAL | Match-Funding (%) | Detailed Budget Assumptions:
Capital Expenditure
|  |  | 0 |  |  |  |  | 0 |  |  | 0 | -
Activity 5. Procurement of Office equipment | Cash | Per unit Cost | 3000 |  |  |  |  | 0 |  | 3000 | 3000 | 100% | Procurement of 3 chairs for AUD 200, 3 desks AUD 800 for new recruits -price quoted
Activity 6. Procurement of Digital cameras for assessment | Cash | Per unit Cost | 148 |  | 296 |  |  | 296 |  | 296 | 592 | 50% | Camera for use in monitoring and evaluating service quality (2 x AUD148 - based on current prices charged by local electronics supplier)
Activity 7. Procurement of Laptops and IT equipment | Cash | Per unit Cost | 1500 | 3000 |  |  |  | 3000 | 3000 |  | 6000 | 50% | 2 laptops required - one for the Project Manager and one for the Project Officer - Based on the current cost of a new laptop from a local in-country electronics supplier - AUD 1,500 per laptop/set of equipment
|  |  | 0 |  |  |  |  | 0 |  |  | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
Capital Expenditure SubTotal: |  |  |  | 3000 | 296 | 0 | 0 | 3296 | 3000 | 3296 | 9592 | 65.64%
Activity | Contribution Type | Unit Type | Unitary Cost (AUD) | Y1S1 | Y1S2 | Y2S1 | Y2S2 | DFAT | Lead Partner | Other Partner(s) | TOTAL | Matched-Funding (%) | Detailed Budget Assumptions:
Program Activity Costs
Activity 6. Conduct demonstration workshop in 8 communities
6.1. Local transport costs for 5 people per 8 workshops | Cash | Per unit Cost | 8 |  | 320 |  |  | 320 |  |  | 320 | 0% | Return trip -based on current market rates
6.2. Accommodation costs for 2 facilitators per 3 nights per 8 workshops | Cash | Daily Cost | 50 |  | 2400 |  |  | 2400 |  |  | 2400 | 0% | Average cost for a 4 star hotel in the region
6.3. Meal costs for 20 people per 8 workshops | Cash | Per unit Cost | 15 |  | 2400 |  |  | 2400 |  |  | 2400 | 0%
Activity 8. Conduct Training to 300 Farmers | [10 empty] | 0 | -
8.1 Per diem costs (5 facilitators @ 3 days* 10 Villages) | Cash | Per unit Cost | 8 |  | 1200 |  |  | 1200 |  |  | 1200 | 0%
8.2. Accommodation costs (5 facilitators@2 hotel nights * 10 villages) | Cash | Daily Cost | 50 |  | 5000 |  |  | 5000 |  |  | 5000 | 0%
8.3. Meal costs for 20 people per 10 villages | Cash | Per unit Cost | 15 |  | 3000 |  |  | 3000 |  |  | 3000 | 0%
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
[11 empty] | 0 | -
Project Activity Costs Sub-Total: |  |  |  | 0 | 14320 | 0 | 0 | 14320 | 0 | 0 | 14320 | 0%
Activity | Contribution Type | Unit Type | Unitary Cost (AUD) | Y1S1 | Y1S2 | Y2S1 | Y2S2 | DFAT | Lead Partner | Other Partner(s) | TOTAL | Match-Funding (%) | Detailed Budget Assumptions:
Other
[9 empty] | 0 |  | 0 | -
[11 empty] | 0 | -
[9 empty] | 0 |  | 0 | -
[10 empty] | 0 | 0 | -
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 | -
|  |  | 0 |  |  |  |  | 0 |  |  | 0 | -
Other Cost Sub-Total: |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
TOTAL BUDGET: |  |  |  | 39660 | 51276 | 36660 | 36660 | 164256 | 166600 | 32096 | 362952 | 54.74%
|  |  |  | Milestone Payment 1 | Milestone Payment 2 | Milestone Payment 3 | Milestone Payment 4
[8 empty] | Cash | 89800 | 32096
[8 empty] | In-Kind | 76800 | 0
|  | Monthly Cost | Cash
|  | Per unit Cost | In-Kind
Annual Cost
Daily Cost
Hourly Cost
Other